## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | mallu neha | 2026-09-15 | OpenCV webcam face tracking stream lag or sllight delay during continuous monitoring session. | Sprint 2 | mallu neha | Logical | Optimized frame capture rate and configured non-blocking release calls. | 2026-09-16 | Closed | Resolved successfully, tested under active webcam stream.
2 | mallu neha | 2026-09-16 | Tab-switch or focus-loss event logging sometimes misses rapid switching triggers. | Sprint 2 | mallu neha | Logical | Updated JavaScript window blur event listeners to capture focus loss accurately. | 2026-09-17 | Closed | Working as expected now.
3 | mallu neha | 2026-09-17 | Streamlit dashboard export summary button formatting issue for JSON logs. | Sprint 2 | mallu neha | User Interface | Fixed data encoding structure for file download handlers. | 2026-09-17 | Closed | Verified export functionality.
4 | mallu neha | 2026-09-17 | Database connection pooling timeout during heavy concurrent exam submissions. | Sprint 2 | mallu neha | Maintainability | Configured SQLite connection reuse execution blocks. | 2026-09-18 | Closed | Performance stabilized under load.
5 | mallu neha | 2026-09-18 | Codebase naming conventions and modular route structure cleanup for admin dashboard. | Sprint 2 | mallu neha | Standards | Refactored Python script functions and applied PEP8 formatting guidelines. | 2026-09-18 | Closed | Code quality checks passed.
6 | mallu neha | 2026-09-18 | Admin warning notification popup styling mismatch across different browser viewports. | Sprint 2 | mallu neha | User Interface | Adjusted CSS media queries and flexbox alignment properties. | 2026-09-18 | Closed | Responsive layout verfied across browsers.
7 | mallu neha | 2026-09-18 | Exception handling for missing or corrupted webcam hardware inputs during system boot. | Sprint 2 | mallu neha | Logical | Added try-except blocks with fallback warning flags in OpenCV frame handler. | 2026-09-18 | Closed | Prevents application crashes on hardware failure.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others